| Sl No | Crop (2015 - 16) | Cropping Area in Ha |  |  |  |  | Production of Seed in Qtl's / Sets in No |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target for the Year | Covered till last Month | Covered during the Month | Cumulative Achievement | Cumulative % of Ach’nt | Target for the Year | Production till last Month | Prd,n during the Month | Cumulative Production | Cumulative % of prd’n Achieved |  |
| 1 | Dhanicha (Green Manuering) | 30.67 | 30.67 | 0.00 | 30.67 | 100% | N/A | N/A | N/A | N/A | N/A | Puddle for green manuering 30.67 Ha |
| 2 | Dhanicha (Seed Production) | 3.50 | 3.50 | 0.00 | 3.50 | 100% | 10.50 | 0.00 | 0.00 | 0.00 | 0% | Seed collection started very poor seed setting. |
| 3 | Maize (AT) Certified Seed (Late Kharif) | 10.81 | 7.00 | 2.53 | 9.53 | 88% | 162.15 | 0.00 | 0.00 | 0.00 | 0% | Sown for Certified seed production in Plot No 19,20,22,23-A,24,27,28-A,B. |
| 4 | Maize (AT) Foundation Seed (Rabi) | 2.98 | 0.00 | 2.98 | 2.98 | 100% | 44.70 | 0.00 | 0.00 | 0.00 | 0% | Sown for Foundation seed production in Plot No 13-A,B & 18- A,B,C. |
| 5 | Sorghum (HC - 136) Foundation Seed (L- Kharif) | 1.15 | 0.17 | 0.76 | 0.93 | 81% | 11.50 | 0.00 | 0.00 | 0.00 | 0% | Sown for Foundation Seed Production in Plot No 26-D,E,F,G,H,I & 25-D. |
| 6 | Sorghum (M35 - 1) Foundation Seed (L- Kharif) | 1.95 | 0.00 | 0.65 | 0.65 | 33% | 23.40 | 0.00 | 0.00 | 0.00 | 0% | Sown for Certified seed production in plot No 21-A&B. |
| 7 | Stylo hamata on Bund's | 1.00 | 1.00 | 0.00 | 1.00 | 100% | 2.00 | 0.00 | 0.00 | 0.00 | 0% | The self germinated plants maintained. |
| 8 | Cow pea (EC 4216) Certified Seeds (Kharif) | 0.47 | 0.47 | 0.00 | 0.47 | 100% | 4.70 | 0.00 | 0.00 | 0.00 | 0% | Poor seed formation ploughed for sowing Oat Trail. |
| 9 | Cow pea (EC 4216) Foundation Seeds (Late Kharif) | 4.61 | 1.63 | 1.23 | 2.86 | 62% | 46.10 | 0.00 | 0.00 | 0.00 | 0% | Foundation in Plot No 4-A & Certified 2-F,3-E,F,G,H ,4-B,26-A,B,C,29-A,B5-A,B. |
| 10 | Cow pea (EC 4216) Foundation Seeds (Rabi) | 3.68 | 0.00 | 0.00 | 0.00 | 0% | 36.80 | 0.00 | 0.00 | 0.00 | 0% |  |
| 11 | Ricebean (Bidhan 1) Foundation Seeds (Kharif) | 0.67 | 0.67 | 0.00 | 0.67 | 100% | 3.35 | 0.00 | 0.00 | 0.00 | 0% | In active growth stage. |
| 12 | Ricebean (Bidhan 1) Certified Seeds (Kharif) | 1.00 | 1.00 | 0.00 | 1.00 | 100% | 5.00 | 0.00 | 0.00 | 0.00 | 0% | In active growth stage . |
| 13 | Oat (Kent) Foundation Seeds (Rabi) | 5.49 | 0.00 | 2.16 | 2.16 | 39% | 65.88 | 0.00 | 0.00 | 0.00 | 0% | Sown in plot No 9-B,C & 12-A. |
| 14 | Bajra (BAIF,Bajra 1) Foundation seed (Summer) | 2.13 | 0.00 | 0.00 | 0.00 | 0% | 25.56 | 0.00 | 0.00 | 0.00 | 0% |  |
|  | Total Area under Seed & BNH | 39.29 | 16.27 | 9.55 | 25.82 | 66% | 441.64 | 0.00 | 0.00 | 0.00 | 0% |  |
| 15 | Hybrid Napier(BNH 10) along internal road | 1.00 | 1.00 | 0.00 | 1.00 | 100% | 10,000,00 | 7,32,200 | 1,20,000 | 8,52,200 | 85% | Plantation maintained for root slip / stems sets production. |
|  | Total Cropping 2015 - 16 | 69.96 | 46.94 | 9.55 | 56.49 | 81% |  |  |  |  |  |  |

MPR of Kalyani Fodder crop Seed & Panting Material Production Farm Chiplima for November 2015

(From 16th October 2015 to 15th November 2015)

Work done during the Month

Sowing of seed crop started with Maize, Cowpea, Sorghum & Oat.

BNH -10 planted along internal road has been harvested & stem cutting has been supplied to CDC.

Proposed work plan for December 2015.

The BNH -10 stumps will be supplied to the CDC.

The sowing of Cowpea & Oat will be continued for seed production.

Harvesting of Daincha for seed.

Dr V K Singh TPE, ODISHA	Rahul Singh Asst Farm Manager,Chiplima	S Jena Farm Manager,Chiplima